## Sheet1
Date | Task Category | Task Details | Deliverables
Nov 16 (Day 1) | Research & Setup | Finalize cultural norms, emotional expressions, and anthropomorphic design principles. | Research documents, confirmed tools & frameworks.
Nov 17-18 (Day 2-3) | Component 1: Social Behaviors | Develop gesture recognition with MediaPipe. Implement culturally adaptive gesture mapping. | Basic gesture recognition system.
Nov 19-20 (Day 4-5) | Component 2: Emotional Expressions | Build emotional recognition pipeline using GANs and Affectiva/OpenFace. Implement detection for basic emotions. | Emotional recognition system detecting basic emotions.
Nov 21-22 (Day 6-7) | Component 3: Voice Communication | Integrate Google Speech-to-Text and Text-to-Speech for voice input/output. Implement emotion-sensitive voice responses. | Basic voice interaction module with emotional sensitivity.
Nov 23 (Day 8) | Review & Sprint 1 Retrospective | Evaluate progress, resolve blockers, and plan integration. | Updated sprint plan with next steps and resolved issues.
Nov 24-26 (Day 9-11) | Integration | Combine gesture, emotional recognition, and voice modules. Test interoperability and optimize performance. | Integrated system prototype.
Nov 27-28 (Day 12-13) | Prototyping the Digital Companion | Create a 3D model using Blender or Unity. Add customizable human-like appearance options. | Basic 3D digital companion with customization features.
Nov 29-30 (Day 14-15) | Testing & Feedback | Test for cultural adaptability, emotion recognition, and voice responses. Collect feedback. | Test results and feedback for improvements.
Dec 1 (Day 16) | Documentation & Presentation | Update technical documentation and prepare a progress presentation for review. | Progress report, system architecture, and presentation slides.

## Sheet2
Date | Component | Task Details | Deliverables
Nov 16 (Day 1) | All Components | Research and Setup: Confirm tools, finalize cultural norms, emotional expressions, and project structure. | Research documents, finalized tools, and frameworks setup.
Nov 17-18 (Day 2-3) | Social Behaviors | Develop gesture recognition with MediaPipe; Implement initial culturally adaptive gestures. | Basic gesture recognition for cultural adaptability.
| Emotional Expressions | Build emotion detection pipeline using GANs and Affectiva/OpenFace; detect basic emotions (e.g., happy, sad). | Emotional recognition for basic emotions.
| Voice Communication | Integrate Google Speech-to-Text and Text-to-Speech; implement basic voice responses. | Voice communication with basic input/output functionality.
| Appearance Design | Use Blender or Unity to create a 3D model; design human-like features with simple customization. | Basic 3D digital companion model with initial human-like design.
Nov 19-20 (Day 4-5) | Social Behaviors | Improve gesture mapping with cultural context; test on sample datasets. | Expanded gesture library with cultural adaptation.
| Emotional Expressions | Test emotion recognition accuracy; refine visual feedback for detected emotions. | Emotion recognition with visual feedback (e.g., facial expressions).
| Voice Communication | Implement dynamic voice responses based on detected emotions; refine voice interactions. | Emotionally sensitive voice interaction module.
| Appearance Design | Enhance 3D model’s features for cultural and role-based design; begin texture rendering. | 3D model with textured rendering and cultural customization.
Nov 21-23 (Day 6-8) | Social Behaviors | Prototype a basic gesture interaction system; ensure smooth transitions between gestures. | Functional prototype for gesture interaction.
| Emotional Expressions | Develop customization features to control emotional response intensity. | Emotion customization panel prototype.
| Voice Communication | Integrate contextual adjustments to voice outputs; test voice system for real-time adaptability. | Voice system responding to emotions in real-time.
| Appearance Design | Integrate real-time design adjustments and finalize role-specific appearance for initial testing. | Prototype with customizable and role-appropriate appearance.
Nov 24-26 (Day 9-11) | All Components | Integration: Combine all components (gestures, emotions, voice, appearance) into a unified system. | Unified digital companion system prototype.
Nov 27-28 (Day 12-13) | All Components | Test the integrated system for cultural adaptability, emotional responsiveness, and usability. | Test results and feedback on the integrated system.
Nov 29-30 (Day 14-15) | All Components | Address issues identified during testing; refine the integrated system and ensure smooth functionality. | Optimized and refined prototype ready for evaluation.
Dec 1 (Day 16) | All Components | Document progress and prepare a comprehensive presentation showcasing 50% completion. | Progress report, updated documentation, and presentation slides.